## Material List
721 NYK |  |  |  | MAIN MATERIAL LIST - LOGISTICS TOOL
Standard view of material list: 1.Sort (A-Z) Part.nr. column F 2.Sort (A-Z) drw.number column R | [15 empty] | DO NOT PRINT -->
Status | NIT Area | Responsibility Area Name | Deck | Denomination | System | Part | Part nr. | Size | Model/Type | Arc.code | Surface | Technical Info | Quant. | Unit | Drawing no. | Weight/Unit | Weigh [KG] | EPD (kg CO2e) | Calorific (MJ/kg) | Calorific (MJ/m2) | Order quant. | Order unit | Extra info | Supplier | Order no. | Delivery week | Delivery place | Received | On board% | NIT_PROJECT_DRAWN WITH
| NA | Staircase & Artwork Mock-up |  | Mock-up |  | 0721_400_O_--_--_--_--_02_40_4010 - 4013
| NA | Staircase & Artwork Mock-up |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| NA | Digital Screen Mock-up |  | Mock-up |  | 0721_400_O_--_--_--_02_40_4020 - 4021
| NA | Digital Screen Mock-up |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| NA | Artwork Display Cabinet Mock-up |  | Mock-up |  | 0721_400_O_--_--_--_03_40_4030
|  | Artwork Display Cabinet Mock-up |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| NA | E Obscure glass door Mock-up |  | Mock-up |  | 0721_400_O_--_11_--_02_58_4010
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| NA | Bi-fold division with housing Mock-up |  | Mock-up |  | 0721_400_O_--_11_--_02_58_4020 - 4021
|  | Bi-fold division with housing Mock-up |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| NA | Media screen wall Mock-up |  | Mock-up |  | 0721_400_O_--_11_--_02_58_4030
|  | Media screen wall Mock-up |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| NA | Bar / Back Bar Mock-up |  | Mock-up |  | 0721_400_O_--_11_--_01_58_4010 - 4012
|  | Bar / Back Bar Mock-up |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| NA | Historia display wall Mock-up |  | Mock-up |  | 0721_400_O_--_11_--_01_58_4020 - 4021
|  | Historia display wall Mock-up |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| NA | Ship model display Mock-up |  | Mock-up |  | 0721_400_O_--_11_--_01_58_4030
|  | Ship model display Mock-up |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| NA | Balustrade with Raised Level and Stair Mock-up |  | Steel Outf. |  | 0721_400_O_--_11_--_01_58_4040 - 4042
|  | Balustrade with Raised Level and Stair Mock-up |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
| 1 | Embarkation and Security Area MVZ 3 DK 3-5 PS SB |  | Lining |  | 0721_400_O_--_--_--_03_40_3150
|  | Embarkation and Security Area MVZ 3 DK 3-5 PS SB |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
| 1 | Embarkation and Security Area MVZ 3 DK 3-5 PS SB |  | Ceiling |  | 0721_400_O_--_--_--_03_40_3120
|  | Embarkation and Security Area MVZ 3 DK 3-5 PS SB |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
| 1 | Embarkation and Security Area MVZ 3 DK 3-5 PS SB |  | Furniture |  | 0721_400_O_--_--_--_03_40_3170
|  | Embarkation and Security Area MVZ 3 DK 3-5 PS SB |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
| 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | 0721_400_O_--_06_--_--_40_3150
|  | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
| 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Ceiling |  | 0721_400_O_--_06_--_--_40_3150
|  | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
| 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Furniture |  | 0721_400_O_--_06_--_--_40_3170
|  | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB" |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
| 3 | Pax Circulation MVZ 3 DK 11 PS SB |  | Lining |  | 0721_400_O_--_11_--_03_40_3150
|  | Pax Circulation MVZ 3 DK 11 PS SB |  | Lining | [12 empty] | 0
|  | Pax Circulation MVZ 3 DK 11 PS SB |  | Lining | [12 empty] | 0
|  | Pax Circulation MVZ 3 DK 11 PS SB |  | Lining | [12 empty] | 0
| 3 | Pax Circulation MVZ 3 DK 11 PS SB |  | Ceiling |  | 0721_400_O_--_11_--_03_40_3120
|  | Pax Circulation MVZ 3 DK 11 PS SB |  | Ceiling | [12 empty] | 0
|  | Pax Circulation MVZ 3 DK 11 PS SB |  | Ceiling | [12 empty] | 0
|  | Pax Circulation MVZ 3 DK 11 PS SB |  | Ceiling | [12 empty] | 0
| 3 | Pax Circulation MVZ 3 DK 11 PS SB |  | Furniture |  | 0721_400_O_--_11_--_03_40_3170
|  | Pax Circulation MVZ 3 DK 11 PS SB |  | Furniture | [12 empty] | 0
|  | Pax Circulation MVZ 3 DK 11 PS SB |  | Furniture | [12 empty] | 0
|  | Pax Circulation MVZ 3 DK 11 PS SB |  | Furniture | [12 empty] | 0
| 4 | Passenger Flow MVZ 2 DK 11 + DK 12 PS SB |  | Lining |  | 0721_400_O_--_--_--_02_40_3250
|  | Passenger Flow MVZ 2 DK 11 + DK 12 PS SB |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
| 4 | Passenger Flow MVZ 2 DK 11 + DK 12 PS SB |  | Ceiling |  | 0721_400_O_--_--_--_02_40_3220
|  | Passenger Flow MVZ 2 DK 11 + DK 12 PS SB |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
| 4 | Passenger Flow MVZ 2 DK 11 + DK 12 PS SB |  | Furniture |  | 0721_400_O_--_--_--_02_40_3270
|  | Passenger Flow MVZ 2 DK 11 + DK 12 PS SB |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
| area number |  |  | Furniture |  | Furniture plan - Pax Circulation MVZ 3 DK 11 PS SB
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
| area number |  |  | Floor |  | Drawing Title
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| area number |  |  | Steel Outf. |  | Steel outfitting plan - Smoking Room MVZ 3 DK 12 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
| area number |  |  | Lining |  | Walls plan - Smoking Room MVZ 3 DK 12
In work | 40 | Smoking Room MVZ 3 DK 12 | 12 | Lining |  | Rectangular Tube | 230 |  | 40x20x1.5x6000 |  | Galvanized |  | 35 | pcs | 0721_400_O_--_12_--_03_40_3151 | 6.8 | 238
In work | 40 | Smoking Room MVZ 3 DK 13 | 12 | Lining |  | Honeycomb Panel | 215,1 |  | 10x1200x2600 | MA-SMO-08 | Laminated |  | 16 | pcs | 0721_400_O_--_12_--_03_40_3151 | 14.2 | 227.2
In work | 40 | Smoking Room MVZ 3 DK 14 | 12 | Lining |  | C-Profile | 212 |  | 20x150x20x2 |  |  |  | 8 | m | 0721_400_O_--_12_--_03_40_3151 | 2.4 | 19.2
In work | 40 | Smoking Room MVZ 3 DK 15 | 12 | Lining |  | Arrow-Profile | 203,1 |  |  | MA-SMO-09 | Painted |  | 16.28 | m | 0721_400_O_--_12_--_03_40_3151 | 0.3 | 4.884
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
| area number |  |  | Ceiling |  | Ceiling plan - Smoking Room MVZ 3 DK 12
In work | 40 | Smoking Room MVZ 3 DK 14 | 12 | Ceiling |  | Rectangular Tube | 330 |  | 40x20x1.5x6000 |  | Galvanized |  | 3 | pcs | 0721_400_O_--_12_--_03_40_3121 | 6.8 | 20.4
In work | 40 | Smoking Room MVZ 3 DK 14 | 12 | Ceiling |  | Ceiling Carrier | 309,1 |  | DAMPA DCC 2000-6000 Modular Carrier No. 16, L=4000 |  |  |  | 7 | pcs | 0721_400_O_--_12_--_03_40_3121 | 3 | 21
In work | 40 | Smoking Room MVZ 3 DK 14 | 12 | Ceiling |  | Ceiling L-List | 317,1 |  | DAMPA DCC 2000-6000 Angle Runner No. 29, L=4000 |  |  |  | 3 | pcs | 0721_400_O_--_12_--_03_40_3121 | 4.2 | 12.6
In work | 40 | Smoking Room MVZ 3 DK 14 | 12 | Ceiling |  | Ceiling Support | P |  | Prefabricated ventilation profile + C list | MA-SMO-01 | Painted |  | 16 | m | 0721_400_O_--_12_--_03_40_3121 | 0
In work | 40 | Smoking Room MVZ 3 DK 14 | 12 | Ceiling |  | Ceiling U-list | 311,1 |  | DAMPA DCC 2000-6000 Edge Trim No. 27, L=4000 | MA-SMO-01 | Painted |  | 3 | pcs | 0721_400_O_--_12_--_03_40_3121 | 2.6 | 7.8
In work | 40 | Smoking Room MVZ 3 DK 14 | 12 | Ceiling |  | Ceiling Z-list | 314,1 |  | DAMPA DCC 2000-6000 Edge Trim No. 26, L=4000 | MA-SMO-01 | Painted |  | 2 | pcs | 0721_400_O_--_12_--_03_40_3121 | 3.2 | 6.4
In work | 40 | Smoking Room MVZ 3 DK 14 | 12 | Ceiling |  | Ceiling Panel | 305,1 |  | DAMPA DCC 2000-6000 Ceiling Panel 3000x600 | MA-SMO-01 | Painted |  | 8 | pcs | 0721_400_O_--_12_--_03_40_3121 | 11.5 | 92
In work | 40 | Smoking Room MVZ 3 DK 14 | 12 | Ceiling |  | Service Hatch | 329,1 |  | DAMPA DCC 6000 inspection hatch 600x600 | MA-SMO-01 | Painted |  | 1 | pcs | 0721_400_O_--_12_--_03_40_3121 | 5 | 5
In work | 40 | Smoking Room MVZ 3 DK 14 | 12 | Ceiling |  | Draught Stop | 341,1 |  | Draught stop h=800 |  |  |  | 14 | m | 0721_400_O_--_12_--_03_40_3121 | 0 | 0
0
0
0
| area number |  |  | Furniture |  | Furniture plan - Smoking Room MVZ 3 DK 12
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
| area number |  |  | Floor |  | Drawing Title
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| area number |  |  | Steel Outf. |  | Steel outfitting plan - Aft Pax Staircase MVZ 3 DK 4-12 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
| area number |  |  | Lining |  | Walls plan - Aft Pax Staircase MVZ 3 DK 4-12 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
| area number |  |  | Ceiling |  | Ceiling plan - Aft Pax Staircase MVZ 3 DK 4-12 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
| area number |  |  | Furniture |  | Furniture plan - Aft Pax Staircase MVZ 3 DK 4-12 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
| area number |  |  | Floor |  | Drawing Title |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| area number |  |  | Steel Outf. |  | Steel outfitting plan - Fore Pax Staircase MVZ 2 DK 4-13 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
| area number |  |  | Lining |  | Walls plan - Fore Pax Staircase MVZ 2 DK 4-13 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
| area number |  |  | Ceiling |  | Ceiling plan - Fore Pax Staircase MVZ 2 DK 4-13 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
| area number |  |  | Furniture |  | Furniture plan - Fore Pax Staircase MVZ 2 DK 4-13 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
| area number |  |  | Floor |  | Drawing Title |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| area number |  |  | Steel Outf. |  | Steel outfitting plan - Passenger Flow MVZ 2 DK 5 PS |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
| area number |  |  | Lining |  | Walls plan - Passenger Flow MVZ 2 DK 5 PS |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
| area number |  |  | Ceiling |  | Ceiling plan - Passenger Flow MVZ 2 DK 5 PS |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
| area number |  |  | Furniture |  | Furniture plan - Passenger Flow MVZ 2 DK 5 PS |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
| area number |  |  | Floor |  | Drawing Title |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| area number |  |  | Steel Outf. |  | Steel outfitting plan - Lecture, Compass Room and Passenger Flow MVZ 2 DK 11 PS |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
| area number |  |  | Lining |  | Walls plan - Lecture, Compass Room and Passenger Flow MVZ 2 DK 11 PS |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
| area number |  |  | Ceiling |  | Ceiling plan - Lecture, Compass Room and Passenger Flow MVZ 2 DK 11 PS |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
| area number |  |  | Furniture |  | Furniture plan - Lecture, Compass Room and Passenger Flow MVZ 2 DK 11 PS |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
| area number |  |  | Floor |  | Drawing Title |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| area number |  |  | Steel Outf. |  | Steel outfitting plan - Lecture, Compass Room and Passenger Flow MVZ 2 DK 11 PS |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
| area number |  |  | Lining |  | Walls plan - Lecture, Compass Room and Passenger Flow MVZ 2 DK 11 PS |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
| area number |  |  | Ceiling |  | Ceiling plan - Lecture, Compass Room and Passenger Flow MVZ 2 DK 11 PS |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
| area number |  |  | Furniture |  | Furniture plan - Lecture, Compass Room and Passenger Flow MVZ 2 DK 11 PS |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
| area number |  |  | Floor |  | Drawing Title |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| area number |  |  | Steel Outf. |  | Steel outfitting plan - Vista Lounge MVZ 1 DK 11 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
| area number |  |  | Lining |  | Walls plan - Vista Lounge MVZ 1 DK 11 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
| area number |  |  | Ceiling |  | Ceiling plan - Vista Lounge MVZ 1 DK 11 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
| area number |  |  | Furniture |  | Furniture plan - Vista Lounge MVZ 1 DK 11 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
| area number |  |  | Floor |  | Raised floor construction plan - Vista Lounge MVZ 1 DK 11 |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| area number |  |  | Mock-up |  | Drawing Title |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
| area number |  |  | Steel Outf. |  | Drawing Title |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
|  |  |  | Steel Outf. | [12 empty] | 0
| area number |  |  | Lining |  | Drawing Title |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
|  |  |  | Lining | [12 empty] | 0
| area number |  |  | Ceiling |  | Drawing Title |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
|  |  |  | Ceiling | [12 empty] | 0
| area number |  |  | Furniture |  | Drawing Title |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
|  |  |  | Furniture | [12 empty] | 0
| area number |  |  | Floor |  | Drawing Title |  |  |  |  | Drawing Name (from drawing list)
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
|  |  |  | Floor | [12 empty] | 0
Note on F3: ====== ID#AAAAxc69hl8 Juhani Määtänen (2023-05-16 05:10:52) Not yet applicable.
Note on G3: ====== ID#AAAAxc69hl0 Juhani Määtänen (2023-05-16 05:10:52) Only parts shown in "Denominations" sheet are allowed. If new part names are to be added, permit from Director, Design & Engineering is needed.
Note on J3: ====== ID#AAAAxc69hlo Juhani Määtänen (2023-05-16 05:10:52) Size / Model / Type added here; sizes and text can be adjusted freely as needed.
Note on K3: ====== ID#AAAAxc69hlw Juhani Määtänen (2023-05-16 05:10:52) Architects color and finishing codes here.
Note on L3: ====== ID#AAAAxc69hlg Juhani Määtänen (2023-05-16 05:10:52) Only surfaces in drop down list are allowed.
Note on M3: ====== ID#AAAAxc69hl4 Juhani Määtänen (2023-05-16 05:10:52) For example color codes, ERP codes, pre-fabrication drawing numbers and any additional info needed.

## Denomination
|  | Renaming of parts listed below is not allowed. |  | Size/Type/Model can be adjusted and modified as necessary | Technical info to include e.g color code, Mars code, door number etc. Any additional information necessary
Denomination | System | Part | Part number | Size / Model / Type | Technical info | Unit | Note
Steel outfitting
|  | A-door | 100 |  | Door Number / Code
|  | Angle bar L30 | 101 | L-bar 30x30
|  | Angle bar L40 | 102 | L-bar 40x40
|  | Beam | 103
|  | Border steel | 104
|  | Bumber | 105
|  | Ceiling bracket | 106
|  | Condence Profile | 107
|  | Deck hatch | 108
|  | Doubling | 109
|  | Flexible Support | 110
|  | Foundation | 111
|  | Handrail | 112
|  | Insulation pin | 113
|  | J-Profile | 114
|  | Metal sheet | 115
|  | Penetration collar | 116
|  | Root plate | 117
|  | Stringer | 118
|  | Step | 119
|  | Storm Rail | 120
|  | Steel plate | 121
|  | Steel sheet | 122
|  | Rectangular Tube | 123
|  | Square Tube | 124
|  | U-Support Profile | 125
|  | Wall support | 126
|  | Washer | 127
|  | WC module | 128
|  | Renaming of parts listed below is not allowed. |  | Size/Type/Model can be adjusted and modified as necessary | Technical info to include e.g color code, Mars code, door number etc. Any additional information necessary
Lining |  | Part | Part number | Size / Model / Type | Technical Info | Unit | Note
|  | Tile Adhesive | 200
|  | A-door | 201 |  | Door Number / Code
|  | A-Glass Door | 202
|  | Arrow-Profile | 203
|  | Arrow-Profile | 203,1 |  | Painted MA-SMO-09 | m |  | 0,3 kg/m
|  | B-15 Movable Wall | 204
|  | B-15 Rock wool Slab | 205
|  | B15-Door | 206
|  | B15-Glass Door | 207
|  | B0-Door | 208
|  | B-Glass Element | 209
|  | C-Door | 210
|  | C-Glass wall | 211
|  | C-Profile | 212 | 20x150x20x2 |  | m |  | 2,4 kg/m
|  | Decorative Profile | 213
|  | Gypsum Board | 214
|  | Honeycomb Panel | 215
|  | Honeycomb Panel | 215,1 | 10x1200x2600 | Laminate MA-SMO-08 | pcs |  | 14,2 kg/pc
|  | J-Profile | 216
|  | LLL Profile | 217
|  | Laminate | 218
|  | L-Profile | 219
|  | Lining Module | 220
|  | Metal Sheet | 221
|  | Moulding | 222
|  | Pillar cover | 223
|  | Roller Shutter | 224
|  | Root plate | 225
|  | Service Hatch | 226
|  | Service Door | 227
|  | Skirting | 228
|  | Sliding door brush seal | 229
|  | Rectangular Tube | 230 | 40x20x1.5x6000 |  | pcs |  | 6,8 kg/pc
|  | Square Tube | 231
|  | Tile Grout | 232
|  | Tile | 233
|  | T-Profile | 234
|  | TV Bracket | 235
|  | U-profile | 236
|  | Ventilation grill | 237
|  | Wall Cassette Bottom Profile | 238
|  | Wall Cassette | 239
|  | Wall Cassette Profile | 240
|  | Wall Cassette Service Hatch | 241
|  | Wall Cassette Service Door | 242
|  | Wall Cassette U-Profile | 243
|  | Wall Cassette Joining Profile | 244
|  | Wall Covering | 245
|  | Wall Paper Glue | 246
Wall Support
|  | Renaming of parts listed below is not allowed. |  | Size/Type/Model can be adjusted and modified as necessary EXAMPLE ONLY | Technical info to include e.g color code, Mars code, door number etc. Any additional information necessary
Ceiling |  | Part | Part number | Size / Model / Type | Technical Info | Unit | Note
|  | Ventilation grill | 300
|  | Angle Bar L40 | 301
|  | Arrow-Profile | 302
|  | Barrisol | 303
|  | Carrier Connection Piece | 304
|  | Ceiling Panel | 305
|  | Ceiling Panel | 305,1 | DAMPA DCC 2000-6000 Ceiling Panel 3000x600 | Painted MA-SMO-01 | pcs |  | 11,5 kg/pc
|  | Ceiling Cassette | 306
|  | Ceiling Module | 307
|  | Ceiling Carrier Lock | 308
|  | Ceiling Carrier | 309
|  | Ceiling Carrier | 309,1 | DAMPA DCC 2000-6000 Modular Carrier No. 16, L=4000 |  | pcs |  | 3 kg/pc
|  | Ceiling Seam List | 310
|  | Ceiling U-list | 311
|  | Ceiling U-list | 311,1 | DAMPA DCC 2000-6000 Edge Trim No. 27, L=4000 | Painted MA-SMO-01 | pcs |  | 2,6 kg/pc
|  | Ceiling U-End list | 312
|  | Ceiling Wall Carrier | 313
|  | Ceiling Z-list | 314
|  | Ceiling Z-list | 314,1 | DAMPA DCC 2000-6000 Edge Trim No. 26, L=4000 | Painted MA-SMO-01 | pcs |  | 3,2 kg/pc
|  | Ceiling Z-insert list | 315
|  | Ceiling Accesories | 316
|  | Ceiling L-List | 317
|  | Ceiling L-List | 317,1 | DAMPA DCC 2000-6000 Angle Runner No. 29, L=4000 |  | pcs |  | 4,2 kg/pc
|  | Ceiling Support | 318
|  | Decorative Profile | 319
|  | Edge Moulding | 320
|  | Front Plate | 321
|  | Flat Ceiling | 322
|  | Gypsum Board | 323
|  | Honeycomb Panel | 324
|  | J-Profile | 325
|  | L-Profile | 326
|  | Metal sheet | 327
|  | Root plate | 328
|  | Service Hatch | 329
|  | Service Hatch | 329,1 | DAMPA DCC 6000 inspection hatch 600x600 | Painted MA-SMO-01 | pcs |  | 5 kg/pc
|  | Rectangular Tube | 330 | 40x20x1.5x6000 |  | pcs |  | 6,8 kg/pc
|  | Square Tube | 331
|  | Support For Camera | 332
|  | Support For Downlight | 333
|  | Support For Exit Light | 334
|  | Support For Lamps | 335
|  | Support For Loudspeaker | 336
|  | Support For Sprinkler | 337
|  | T-Profile | 338
|  | U-insert profile | 339
|  | Z-Profile | 340
|  | Draught Stop | 341
|  | Draught Stop | 341,1 | Draught stop h=800 |  | m |  | kg/m
|  | B-15 Extension | 342
|  | Exit light | 343
|  | Renaming of parts listed below is not allowed. |  | Size/Type/Model can be adjusted and modified as necessary | Technical info to include e.g color code, Mars code, door number etc. Any additional information necessary
Floor |  | Part | Part number | Size / Model / Type | Technical Info | Unit | Note
|  | Angle Bar L40 | 400 | L-bar 40x40
|  | Angle Bar L50 | 401 | L-bar 50x50
|  | Border Profile | 402
|  | Carpet Adhesive | 403
|  | Carpet | 404
|  | Cement Compound | 405
|  | Cove Profile | 406
|  | Anti-slip Tape | 407
|  | Synthetic Floor | 408
|  | Drain cover | 409
|  | Dirt Mat | 410
|  | Epoxy | 411
|  | Flat bar | 412
|  | Floating Floor | 413
|  | Floor Module | 414
|  | Levelling | 415
|  | Light Concrete | 416
|  | Rockwool | 417
|  | Skirting | 418
|  | Square Bar | 419
|  | Support Flat Bar | 420
|  | Support Flat Piece | 421
|  | Support Plate | 422
|  | Stair Nosing Profile | 423
|  | Steel Plate | 424
|  | Steel Sheet | 425
|  | Plywood | 426
|  | Parquet Adhesive | 427
|  | Painted Floor | 428
|  | Pedimat | 429
|  | Teak | 430
|  | Threshold | 431
|  | Tile | 432
|  | Tile Adhesive | 433
|  | Tile Grout | 434
|  | Tile Cove | 435
|  | Tile Cove Corner | 436
|  | Vinyl Floor | 437
|  | Vinyl Adhesive | 438
|  | Visco | 439
|  | Underlay | 440
|  | U-Profile | 441
|  | Water insulation | 442
|  | Renaming of parts listed below is not allowed. |  | Size/Type/Model can be adjusted and modified as necessary | Technical info to include e.g color code, Mars code, door number etc. Any additional information necessary
Furniture |  | Part | Part number | Size / Model / Type | Technical Info | Unit | Note
Note on B39: ====== ID#AAAAxc69hls Juhani Määtänen (2023-05-16 05:10:52) NIT Denomination: Steel outfitting, Lining, Ceiling, Floor, Furniture
Note on D39: ====== ID#AAAAxc69hlk Juhani Määtänen (2023-05-16 05:10:52) Part Name, to be selected from the list. If new part names needs to be added, permission from Director Design & Engineering is needed

## Door list
[11 empty] | Project: | [10 empty] | Update:
Order number:
Filled by procurement / supplier
Cost center | Pos. no. | Area | Deck | Dwg part no. | Pos | Door no. | Delivery time | Door Type | Frame type | HIB |  | Clear opening |  |  | Door frame | [5 empty] | PKL | Hinge (L / R) | Lock cutout | Lock type | Escutcheon cut-out | Handle cut-out | Door closer / operator | Doorleaf |  |  | Frame |  | Window | Kick plate | Push plate | Remarks | Quantity of doors | Price, €
[10 empty] | W | H | Y1 | Y2 | Z | Sill type | Sill height ( T ) | Air Gap ( V ) | Height of top piece ( C ) | Bhd thk ( S ) | Tot. Height ( F) | [7 empty] | Hinge (Side 1) | Opposite (Side 2) | Trimlist | Frame hinge side (side 1) | Frame opposite side (side 2)
Sundeck | 1 | 175U_T_F | 17 |  | Single | 4621.175U.170707C | 19 | C | Z |  |  | 700 |  | 2000 |  | 20 | 6 | 20 | 50 |  | 1050 | L | TV5316/8 | WC | TV7562 | TV 7363/8 + TV 7509 | Dorma TS83 | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO |  |  |  | self-closing | 1
Sundeck | 2 | 175U_T_F | 17 |  | Single | 4621.175U.170707B | 19 | C | Z |  |  | 700 |  | 2000 |  | 20 | 6 | 20 | 50 |  | 1050 | R | TV5316/8 | WC | TV7562 | TV 7363/8 + TV 7509 | Dorma TS83 | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO |  |  |  | self-closing | 1
Sundeck | 3 | 167Y_T | 16 |  | Single | 4621.167Y.160717A | 19 | B | Z |  |  | 800 |  | 2000 |  | 20 | 6 | 20 | 65 |  | 1050 | R | TV5316/8 | UL | TV5966 | TV 7363/8 + TV 7509 | Dorma ED100/250 | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO |  |  |  | automatic, M/M | 1
Sundeck | 4 | 167Y_T | 16 |  | Single | 4621.167Y.160707A | 19 | B | Z |  |  | 800 |  | 2000 |  | 20 | 6 | 20 | 65 |  | 1050 | R | TV5316/8 | UL | TV5966 | TV 7363/8 + TV 7509 | Dorma ED100/250 | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO | Tiger Coatings: 29/79195 Mica 17 ME/MATT/CO |  |  |  | automatic, M/M | 1
Sundeck | 5 | 167Y_K | 16 | 52 | Double | 4621.167Y.160723 | 19 | B | Z |  |  | 950 | 950 | 2000 |  | 20 | 6 | 20 | 50 |  | 1050 | R | TV5316/8 | LO/1 | TV5968 | TV 7363/8 + TV 7509 | Dorma TS83 | laminate KT-WC-1105: Pfleiderer U11077 VV | NCS S 0505-Y20R | RAL 9016 | RAL 9016 | NCS S 0505-Y20R |  |  |  | self-closing, corner latches | 1
Sundeck | 6 | 167Y_K | 16 | 53 | Single | 4621.167Y.160704 | 19 | B | Z |  |  | 950 |  | 2000 |  | 20 | 6 | 20 | 160 |  | 1050 | R | TV5316/8 | LO/B | TV5968 | TV 7363/8 + TV 7509 | Dorma ED100/250 | KT-PT-1100: RAL 9016 | KT-WC-1105: Pfleiderer U11077/VV | RAL 9016 | RAL 9016 | RAL 9016 |  |  |  | automatic, M/M | 1
Sundeck | 7 | 167Y_K | 16 | 54 | Single | 4621.167Y.160721 | 19 | B | Z |  |  | 950 |  | 2000 |  | 20 | 6 | 20 | 160 |  | 1050 | L | TV5316/8 | LO/B | TV5968 | TV 7363/8 + TV 7509 | Dorma ED100/250 | KT-PT-1100: RAL 9016 | KT-WC-1105: Pfleiderer U11077/VV | RAL 9016 | RAL 9016 | RAL 9016 |  |  |  | automatic, M/M | 1
Sundeck | 8 | 167Y_K | 16 | 55 | Single | 4621.167Y.160722 | 19 | B | Z |  |  | 950 |  | 2000 |  | 20 | 6 | 20 | 160 |  | 1050 | L | TV5316/8 | LO/2 + WC indicator | TV7562 | TV 7363/8 + TV 7509 | Dorma ED100/250 | KT-PT-1100: RAL 9016 | KT-PT-1108: RAL 440-1 (high glossy 70-80%) | RAL 440-1 (high glossy 70-80%) | RAL 9016 | RAL 440-1 (high glossy 70-80%) |  |  |  | automatic, M/M with WC-indicator light + locking | 1
Sundeck | 9 | 167Y_K | 16 | 56 | Single | 4621.167Y.160705B | 19 | B | Z |  |  | 900 |  | 2000 |  | 20 | 6 | 20 | 120 |  | 1050 | L | TV5316/8 | LO/2 | TV5968 | TV 7363/8 + TV 7509 | Dorma TS83 | NCS S 0505-Y20R | KT-PT-1107: NCS S 0520-Y20R | NCS S 0520-Y20R | NCS S 0505-Y20R | KT-PT-1107: NCS S 0520-Y20R |  |  |  | self-closing | 1
Sundeck | 10 | 167Y_K | 16 | 57 | Single | 4621.167Y.160705A | 19 | B | Z |  |  | 900 |  | 2000 |  | 30 | 6 | 20 | 150 |  | 1050 | L | TV5316/8 | LO/1 | TV5968 | TV 7363/8 + TV 7509 | Dorma TS83 | KT-PT-1108: RAL 440-1 (high glossy 70-80%) | NCS S 0505-Y20R | RAL 440-1 (high glossy 70-80%) | RAL 440-1 (high glossy 70-80%) | NCS S 0505-Y20R |  |  |  | self-closing | 1
Sundeck | 11 | 167Y_F | 16 | 64 | Double | 4622.167Y.160715A | 19 | C | Z |  |  | 600 | 600 | 2000 |  | 20 | 6 | 20 | 95 |  | 1050 | L | TV5316/8 | LO/1 | TV5968 | TV 7363/8 + TV 7509 | - | PT-802: NCS S 1050-Y30R | PT-801: NCS S 0804-Y30R | PT-801: NCS S 0804-Y30R | PT-801: NCS S 0804-Y30R | PT-801: NCS S 0804-Y30R |  |  |  | FCU-gasket for sound reduction, corner latches | 1
Crew | 12 | 165Y | 16 |  | Single | 4622.165Y.160619 | 18 | C | Z |  |  | 950 |  | 2000 |  | 20 | 6 | 20 | 45 |  | 1050 | L | TV Sign ANSI | LO/1+CR | TV Sign ANSI | TV Sign ANSI | Dorma TS83 | RAL 9010 | RAL 9010 | RAL 9010 | RAL 9010 | RAL 9010 |  |  |  | self-closing | 1
Crew | 13 | ST61 | 3 |  | Single | 4621.ST61.030630 | 18 | B | Z |  |  | 800 |  | 2000 |  | 20 | 6 | 20 | 90 |  | 1050 | L | TV5133 | FP | TV5968 | to be design by Tammer | Dorma TS83 | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R |  |  |  | Side2: Finger print controller | 1
Crew | 14 | ST61 | 3 |  | Single | 4621.ST61.030629 | 18 | B | Z |  |  | 800 |  | 2000 |  | 20 | 6 | 20 | 90 |  | 1050 | L | TV5133 | FP | TV5968 | to be design by Tammer | Dorma TS83 | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R |  |  |  | Side2: Finger print controller | 1
Crew | 15 | ST61 | 3 |  | Single | 4621.ST61.030628 | 18 | B | Z |  |  | 800 |  | 2000 |  | 20 | 6 | 20 | 90 |  | 1050 | L | TV5316/8 | LO/2 | TV5968 | TV 7363/8 + TV 7509 | Dorma TS83 | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R |  |  |  | Side1: TV ANSI card reader | 1
Crew | 16 | ST61 | 3 |  | Single | 4621.ST61.030627 | 18 | B | Z |  |  | 800 |  | 2000 |  | 20 | 6 | 20 | 90 |  | 1050 | R | TV5316/8 | LO/2 | TV5968 | TV 7363/8 + TV 7509 | Dorma TS83 | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R |  |  |  |  | 1
Crew | 17 | ST61 | 3 |  | Single | 4621.ST61.030626 | 18 | B | Z |  |  | 800 |  | 2000 |  | 20 | 6 | 20 | 90 |  | 1050 | L | TV5316/8 | LO/2 | TV5968 | TV 7363/8 + TV 7509 | Dorma TS83 | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R |  |  |  |  | 1
Crew | 18 | ST61 | 3 |  | Double | 4621.ST61.030623 | 18 | B | Z |  |  | 900 | 300 | 2000 |  | 20 | 6 | 20 | 90 |  | 1050 | R | TV5316/8 | UL | TV5966 | TV 7363/8 + TV 7509 | Dorma TS83 | NCS S 0505-Y20R | RAL 9010 | NCS S 0505-Y20R | NCS S 0505-Y20R | RAL 9010 |  |  |  |  | 1
Crew | 19 | ST41 | 4 |  | Double | 4621.ST41.040401 | 18 | B | Z |  |  | 900 | 350 | 2000 |  | 20 | 6 | 20 | 90 |  | 1050 | R | TV5316/8 | UL | TV5966 | TV 7363/8 + TV 7509 | Dorma TS83 | RAL 9010 | NCS S 2070-Y40R | AISI 304 Brushed | RAL 9010 | NCS S 2070-Y40R |  |  |  |  | 1
Sundeck | 20 | 192U | 19 | 15 | Single | 192U_15.1 | 19 | C | Z |  |  | 700 |  | 2000 |  | 25 | 6 | 20 | 90 |  | 1050 | R | TV5316/8 | UL | TV5966 | TV 7363/8 + TV 7509 | Dorma TS83 | RAL 9016 | RAL 9016 | RAL 9016 | RAL 9016 | RAL 9016 |  |  |  | self-closing | 1
Sundeck | 21 | 192U | 19 | 15 | Single | 192U_15.2 | 19 | C | Z |  |  | 700 |  | 2000 |  | 25 | 6 | 20 | 90 |  | 1050 | R | TV5316/8 | UL | TV5966 | TV 7363/8 + TV 7509 | Dorma TS83 | RAL 9016 | RAL 9016 | RAL 9016 | RAL 9016 | RAL 9016 |  |  |  | self-closing | 1
Crew | 22 | ST61 | 3 |  | Single | 4621.ST61.030602 | 18 | B | Z |  |  | 800 |  | 2000 |  | 20 | 6 | 20 | 45 |  | 1050 | R | TV5133 | LO/01+FP | TV5968 | to be design by Tammer | Dorma TS83 | RAL 9010 | RAL 9010 | RAL 9010 | RAL 9010 | RAL 9010 |  |  |  |  | 1
Crew | 23 | 034N | 3 |  | Single | 4621.034N.030410 | 18 | B | Z |  |  | 900 |  | 2000 |  | 20 | 6 | 20 | 90 |  | 1050 | R | TV5316/8 | UL | TV5966 | TV 7363/8 + TV 7509 | Dorma TS83 | RAL 9010 | RAL 9010 | RAL 9010 | RAL 9010 | RAL 9010 |  |  |  |  | 1
Crew | 24 | 034N | 3 |  | Single | 4621.034N.030402 | 18 | B | Z |  |  | 900 |  | 2000 |  | 20 | 6 | 20 | 90 |  | 1050 | R | TV5316/8 | UL | TV5966 | TV 7363/8 + TV 7509 | Dorma TS83 | RAL 9010 | RAL 9010 | RAL 9010 | RAL 9010 | RAL 9010 |  |  |  |  | 1
Crew | 25 | ST41 | 4 |  | Single |  | 19 | B | Z |  |  | 700 |  | 1900 |  | 20 | 6 | 20 | - |  | 1050 | L | TV5341 | LO/1 | TV5522 |  | Dorma TS83 | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R | NCS S 0505-Y20R |  |  |  |  | 1
Crew | 26 | ST61 |  |  | Single |  | 19 | C | Z |  |  | 700 |  | 1900 |  | 20 | 6 | 20 | - |  | 1050 | R | TV5341 | LO/1 | TV5522 |  | Dorma TS83 | RAL 9010 | RAL 9010 | RAL 9010 | RAL 9010 | RAL 9010 |  |  |  |  | 14
Crew | 27 | ST11, ST22, ST41 |  |  | Single |  | 19 | C | Z |  |  | 700 |  | 1900 |  | 20 | 6 | 20 | - |  | 1050 | L | TV5341 | LO/1 | TV5522 |  | Dorma TS83 | RAL 9010 | RAL 9010 | RAL 9010 | RAL 9010 | RAL 9010 |  |  |  |  | 43
Crew | 28 | ST41 | 7 |  | Double | 4622.ST41.070404A | 18 | C | Z |  |  | 1000 | 1000 | 2500 |  | 20 | 6 | 20 | 65 |  | 1050 | R | TV5316/8 | UL | TV5966 | TV 7363/8 + TV 7509 | Dorma TS83 | Primer | RAL 9010 | Primer | Primer | RAL 9010 |  |  |  |  | 1
Sundeck | 29 | 175U_P | 17 |  | Single | 4622.175U.170623B | 19 | C | Z |  |  | 650 |  | 2000 |  | 20 | 6 | 20 | 50 |  | 1050 | L | TV5316/8 (AISI 316) | UL | TV5966 (AISI 316) | TV 7363/8 + TV 7509 (AISI 316) | Dorma TS83 (AISI 316) | AISI 316 RAL 9016 | AISI 316 RAL 9016 | AISI 316 RAL 9016 | AISI 316 RAL 9016 | AISI 316 RAL 9016 |  |  |  | self-closing, door and lock case to be seaweather resistant and water-insulated! | 1
Sundeck | 30 | 175U_P | 17 |  | Single | 4622.175U.170612C | 19 | C | Z |  |  | 650 |  | 2000 |  | 20 | 6 | 20 | 50 |  | 1050 | R | TV5316/8 (AISI 316) | UL | TV5966 (AISI 316) | TV 7363/8 + TV 7509 (AISI 316) | Dorma TS83 (AISI 316) | AISI 316 RAL 9016 | AISI 316 RAL 9016 | AISI 316 RAL 9016 | AISI 316 RAL 9016 | AISI 316 RAL 9016 |  |  |  | self-closing, door and lock case to be seaweather resistant and water-insulated! | 1
0
T = Still height | [22 empty] | DELIVERY INCLUDES |  |  |  |  | NIT PURCHASE
V = Air gap doorleaf / sill | [22 empty] | Lock-cutout |  |  |  |  | Escutcheons
S = Bulkhead thickness | [22 empty] | Card lock ANSI Signature ANSI |  |  |  |  | Handles
F = Total height | [22 empty] | "Finger Print" (FP) |  |  |  |  | Indicator Roses
C = Height of top piece | [22 empty] | Dorma ED100 |  |  |  |  | Door closer Dorma TS83
PK = Handle height (from top of doorlleaf) | [22 empty] | Flatscan SW safety sensor
PKL = Handle height (from under the sill) | [22 empty] | Magic Switch Touchless
HIB = Hole in bulkhead | [22 empty] | ADA Switch (staff WC)
Red-Green light indicator
[28 empty] | Sliding door operators |  |  |  |  | R = RADAR: DOR-86711400 Tutka+turva, Opti combi EN16005 Saranaovi: AMS-EAGLE1-MUSTA Mikroaaltotutka eagle1
P = PUSH BUTTON: type pending
M = MAGIC SWITCH (Touchless): Dor-7030000021403 CleanSwitch tutkakytkin
F = PUSH BUTTON FOOT: Dor- 16673101170 Jalkakytkin LED
LF = LED FOOD BUTTON (IP69): Dor- 16672901170 Glas LED Sensortaster + LED kytkimen soviterengas upporasialle Dor-16672701170
L = LED PUSH BUTTON: Dor- 16672601170 LED kytkin muovikehällä + LED kytkimen soviterengas upporasialle Dor-16672701170
LD = LED PUSH BUTTON MINI ON LEAF: Dor-16672301170 Mini LED kytkin
Emergency Switch

## List
Surfaces | Status | Ceiling | Walls | Floor | Steel outfitting | Certificate | Prefab.
Galvanized |  | Ventilation grill | Tile Adhesive | Anti-slip Tape | Angle bar L30 | MED | YES
Painted | In work | Angle Bar L40 | A-door | Angle Bar L40 | Angle bar L40 | Noncombust. | NO
Anodized | Engineered | Arrow-Profile | A-Glass Door | Angle Bar L50 | Beam | Type Approval
Brushed | Inquired | Barrisol | Arrow-Profile | Border Profile | Border steel | ADA complient
Electrogalvanization | Ordered | Carrier Connection Piece | B0-Door | Carpet Adhesive | Bumber | Marine use
Laminated | Received | Carrier Connection Piece | B-15 Movable Wall | Carpet | Ceiling bracket
Coated | On Board | Ceiling Panel | B-15 Rock wool Slab | Cement Compound | Condence Profile
Primer | Not In Use | Ceiling Cassette | B15-Door | Cove Profile | Deck hatch
Foiled | Owner/Yard | Ceiling Module 1 | B15-Glass Door | Drain cover | Doubling
Wall Covering | Partly received | Ceiling Module 2 | B-Glass Element | Dirt Mat | Flat bar
NA | Partly On Board | Ceiling Module 3 | C-Door | Epoxy | Flexible Support
Barrisol |  | Ceiling Module 4 | C-Glass wall | Flat bar | Foundation
Vinyl |  | Ceiling Module 5 | C-Glass door | Floating floor | Handrail
Galvanized / Foiled |  | Ceiling Module 6 | C-Profile | Floor Module 1 | Insulation pin
Galvanized / Primered |  | Ceiling Module 7 | Decorative Profile | Floor Module 2 | J-Profile
Galvanized / Painted |  | Ceiling Module 8 | Gypsum Board | Floor Module 3 | Metal sheet
Galvanized / Foiled |  | Ceiling Module 9 | Honeycomb Panel | Floor Module 4 | Penetration collar
Galvanized both sides | In work | Ceiling Module 10 | J-Profile | Floor Module 5 | Root plate
Primered both sides | Engineered | Ceiling Carrier Lock | LLL Profile | Floor Module 6 | Stringer
Painted both sides | Inquired | Ceiling Carrier | L-Profile | Floor Module 7 | Step
Foiled both sides | Offer received | Ceiling Seam List | Lining Module 1 | Floor Module 8 | Square Tube
|  | Ceiling Wall Carrier | Lining Module 2 | Floor Module 9 | Steel plate
|  | Ceiling Z-list | Lining Module 3 | Floor Module 10 | Steel sheet
|  | Ceiling Accesories | Lining Module 4 | Levelling | Storm Rail
|  | Ceiling L-List | Lining Module 5 | Light concrete | Rectangular Tube
|  | Ceiling Support | Lining Module 6 | Rockwool | U-Support Profile
|  | Ceiling U-list | Lining Module 7 | Skirting | Wall support
|  | Ceiling U-End list | Lining Module 8 | Square Bar | Wall bracket
|  | Ceiling Z-list | Lining Module 9 | Support Flat Bar | WC module
|  | Ceiling Z-insert list | Lining Module 10 | Support Flat Piece | Washer
|  | Ceiling Accesories | Metal Sheet | Support Plate
|  | Ceiling L-List | Pillar cover | Stair Nosing Profile
|  | Ceiling Support | Rectangular Tube | Steel plate
|  | Decorative Profile | Roller Shutter | Steel sheet
|  | Edge Moulding | Root plate | Synthetic Floor
|  | Front Plate | Painted steel | Plywood
|  | Flat Ceiling | Service Hatch | Painted Floor
|  | Gypsum Board | Service Door | Teak
|  | Honeycomb Panel | Sliding door brush seal | Threshold
|  | J-Profile | Skirting | Tile
|  | L-Profile | Square Tube | Tile Adhesive
|  | Metal sheet | Tile Grout | Tile Grout
|  | Painted steel | Tiles | Tile Cove
|  | Rectangular Tube | T-Profile | Tile Cove Corner
|  | Root plate | TV Bracket | U-Profile
|  | Service Hatch | U-profile | Underlay
|  | Square Tube | Ventilation grill | Vinyl Floor
|  | Support For Camera | Wall Cassette Bottom Profile | Vinyl Adhesive
|  | Support For Downlight | Wall Cassette | Water Insulation
|  | Support For Exit Light | Wall Cassette Profile | Visco
|  | Support For Lamps | Wall Cassette Service Hatch
|  | Support For Loudspeaker | Wall Cassette Service Door
|  | Support For Sprinkler | Wall Cassette U-Profile
|  | T-Profile | Wall Cassette Joining Profile
|  | U-insert profile | Wall Covering
|  | Z-Profile | Wall Paper Glue
|  | Draught Stop | Wall Support
B-15 Extension
Exit light

## Summary
Summary of Material List Project xxxxx
Status | Overall % | Number of Rows
In work | 4.643% | 13
Engineered | 0% | 0
Inquired | 0% | 0
Ordered | 0% | 0
Owner/Yard | 0% | 0
Received | 0% | 0
On Board | 0% | 0
Not In Use | 0% | 0
Empty | 95.36% | 267
Total Row | 100% | 280
Estimated Rows

## Preliminary Material List (for
721 NYK |  |  |  |  | PRELIMINARY MATERIAL LIST - FOR ENQUIRIES
Standard view of material list: 1.Sort (A-Z) Part.nr. column F 2.Sort (A-Z) drw.number column R | [20 empty] | DO NOT PRINT -->
Status | MW Area | NIT Area | Responsibility Area Name | Deck | Denomination | System | Part | Part nr. | Size | Technical Info | Arc.code | Surface | Comments | EPD Value | Caloric value | Certificate | Quant. | Unit | Prefab. | Prefab drawing no. | Weight/Unit | Weigh [KG] | Order quant. | Order unit | Extra info | Supplier | Order no. | Delivery week | Delivery place | Received | On board%
| 40 | 1 | Embarkation and Security Area MVZ 3 DK 3-5 PS SB |  | Lining |  | 0721_400_O_--_--_--_03_40_3150
|  |  | Embarkation and Security Area MVZ 3 DK 3-5 PS SB |  | Lining | [16 empty] | 0
[5 empty] | Lining | [16 empty] | 0
[5 empty] | Lining | [16 empty] | 0
| 40 | 1 | Embarkation and Security Area MVZ 3 DK 3-5 PS SB |  | Ceiling |  | 0721_400_O_--_--_--_03_40_3120
|  |  | Embarkation and Security Area MVZ 3 DK 3-5 PS SB |  | Ceiling | [16 empty] | 0
[5 empty] | Ceiling | [16 empty] | 0
[5 empty] | Ceiling | [16 empty] | 0
| 40 | 1 | Embarkation and Security Area MVZ 3 DK 3-5 PS SB |  | Furniture |  | 0721_400_O_--_--_--_03_40_3170
|  |  | Embarkation and Security Area MVZ 3 DK 3-5 PS SB |  | Furniture | [16 empty] | 0
[5 empty] | Furniture | [16 empty] | 0
[5 empty] | Furniture | [16 empty] | 0
| 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | 0721_400_O_--_06_--_--_40_3150
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | Hardcore Panel |  | 1200x2500x10 | Hardcore wall lining | MA-PAS-14 | Laminated | laminate listed separately |  |  | Noncombust. | 66 | m2 | NO |  | 5 | 330
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | Hardcore Panel |  | 1200x2500x10 | Hardcore wall lining | MA-PAS-04 | Wall Covering | wall covering listed separately |  |  | Noncombust. | 369 | m2 | NO |  | 5 | 1845
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | Wall Cassette |  | 600x2300x25 | B15 Cassette wall lining + profiles | NA | Foiled | Gislaved foil 1320-103-F06A NCS S 0603-Y40R, matt Check the Wismar warehouse |  |  | Noncombust. | 72 | m2 | NO |  | 17 | 1224
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | Wall Cassette |  | 600x2300x25 | B15 Cassette sound insulation | NA | NA | Chech the Wismar warehouse |  |  | Noncombust. | 69 | m2 | NO |  | 23 | 1587
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | Laminate |  | 1200x2500x10 | BORNEO BOA301 | MA-PAS-14 |  |  |  |  | Noncombust. | 66 | m2 | NO |  | 1 | 66
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | Wall Covering |  | 1200x2500x10 | ARTE NEON 67062 | MA-PAS-04 |  |  |  |  | Noncombust. | 369 | m2 | NO |  | 1 | 369
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | B-15 Wall extension |  | 600x2300x25 | Rockwool or cassette | NA |  | Check the Wismar warehouse |  |  | Noncombust. |  | m2 | NO |  | 17 | 0
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | B15-Door |  | 600x2300x25 | Hinged, single, CW750, self-closer | NA | Wall Covering | Door handle ASSA ABLOY VINGCARD TV 7363 S/8 satin brass |  |  | Noncombust. | 5 | pcs | NO |  | 60 | 300
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | B15-Door |  | 600x2300x25 | Sliding, CW1000, el. driven | NA | Wall Covering | el. drive system from Dorma delivered by Yard |  |  | Noncombust. | 3 | pcs | NO |  | 80 | 240
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | B15-Door |  | 600x2300x25 | Sliding, CW700, el. driven | NA | Wall Covering | el. drive system from Dorma delivered by Yard |  |  | Noncombust. | 2 | pcs | NO |  | 65 | 130
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | C-Door |  | 600x2300x25 | Hinged, single, CW800 | NA | Foiled | Door handle ASSA ABLOY VINGCARD TV 7363 S/8 satin brass |  |  | Noncombust. | 1 | pcs | NO |  | 55 | 55
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | Decorative Profile |  | 600x2300x25 | Columns between windows PF deck 6 | NA |  |  |  |  | Noncombust. | 20 | set | YES | 0721_400_O_--_06_--_--_40_3154 |  | 0
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | Service Hatch |  | 600x2300x25 | 500x750, triangle lock, for hardcore walls | NA | Wall Covering | ARTE NEON 67062 |  |  | Noncombust. | 5 | pcs | NO |  | 5 | 25
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | Service Hatch |  | 600x2300x25 | 500x750, triangle lock, for cassette walls | NA | Wall Covering | Gislaved foil 1320-103-F06A |  |  | Noncombust. | 2 | pcs | NO |  | 5 | 10
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | Service Door |  | 600x2300x25 | FCU double door 1700x2000, triangle lock, for hardcore walls | NA | Wall Covering | ARTE NEON 67062 |  |  | Noncombust. | 1 | pcs | NO |  |  | 0
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | Arrow-Profile |  | 600x2300x25 |  | MA-PAS-14 | Painted | as small as it gets |  |  | Noncombust. | 43 | pcs | NO |  |  | 0
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Lining |  | Wall Support |  | 600x2300x25 | Tube 20x40x1,5 st. | NA | Galvanized |  |  |  | Noncombust. | 1558 | m | NO |  | 1 | 1558
| 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Ceiling |  | 0721_400_O_--_06_--_--_40_3150
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Ceiling |  | Panel Ceiling |  |  | DCC 308 Dampa 275+25mm or similar, C | NA | Painted | NCS S 0502 - Y50R matt Check the Wismar warehouse |  |  |  | 19 | m2 | NO |  | 7 | 133
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Ceiling |  | Decorative Profile |  |  | Airgap sofit profile | MA-PAS-02 | Painted | NCS OFF-WHITE PAINT FINISH S 0502 Y MATT |  |  |  |  | m | YES | P0721_CEILING_40_51 |  | 0
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Ceiling |  | Decorative Profile |  |  | Sofit filler profile | MA-PAS-02 | Painted | NCS OFF-WHITE PAINT FINISH S 0502 Y MATT |  |  |  |  | m | YES | P0721_CEILING_40_52 |  | 0
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Ceiling |  | Decorative Profile |  |  | Window LED G-profile | MA-PAS-02 | Painted | NCS OFF-WHITE PAINT FINISH S 0502 Y MATT |  |  |  |  | m | YES | P0721_CEILING_40_53 |  | 0
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Ceiling |  | Decorative Profile |  |  | Window curtain profile | MA-PAS-02 | Painted | NCS OFF-WHITE PAINT FINISH S 0502 Y MATT |  |  |  |  | m | YES | P0721_CEILING_40_54 |  | 0
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Ceiling |  | Cassette Ceiling |  |  | Lautex TJ-TYPE 600 or similar, AL, C | MA-PAS-01 | Painted | NCS OFF-WHITE PAINT FINISH S 0502 Y MATT |  |  |  | 126 | m2 | NO |  | 3 | 378
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Ceiling |  | Flat Ceiling |  |  | Hardocre panel based | MA-PAS-02 | Painted | NCS OFF-WHITE PAINT FINISH S 0502 Y MATT |  |  |  | 29 | m2 | NO |  | 5 | 145
In work | 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Ceiling |  | Ceiling Support |  |  | Tube 20x40x1,5 st. | NA | Galvanized |  |  |  |  | 281 | m | NO |  | 1 | 281
| 40 | 2 | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB |  | Furniture |  | 0721_400_O_--_06_--_--_40_3170
In work |  |  | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB" |  | Furniture |  | Curtain rail |  |  | L=2200 | NA | [5 empty] | 14 | pcs | NO |  |  | 0
In work |  |  | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB" |  | Furniture |  | Curtain |  |  | L=1100 H=? | WT-PAS-001 |  | MAIN FABRIC - sekkers liro 24 ink LINING FABRIC - edmund bell outblack silk fr seal |  |  |  | 14 | pcs | NO |  |  | 0
In work |  |  | Passenger Flow_Hotel Store and Lockers MVZ 3-5 DK 6 PS SB" |  | Furniture |  | Handrail |  |  | dia 38mm leather effect foil | MA-PAS-18 | Foiled | RENOLIT LEATHER EFFECT FOIL - WELSH BROWN S40.60.03.0275 |  |  |  | 34.5 | m | NO |  | 2 | 69
| 40 | 3 | Pax Circulation MVZ 3 DK 11 PS SB |  | Lining |  | 0721_400_O_--_11_--_03_40_3150
|  |  | Pax Circulation MVZ 3 DK 11 PS SB |  | Lining | [16 empty] | 0
|  |  | Pax Circulation MVZ 3 DK 11 PS SB |  | Lining | [16 empty] | 0
|  |  | Pax Circulation MVZ 3 DK 11 PS SB |  | Lining | [16 empty] | 0
| 40 | 3 | Pax Circulation MVZ 3 DK 11 PS SB |  | Ceiling |  | 0721_400_O_--_11_--_03_40_3120
|  |  | Pax Circulation MVZ 3 DK 11 PS SB |  | Ceiling | [16 empty] | 0
|  |  | Pax Circulation MVZ 3 DK 11 PS SB |  | Ceiling | [16 empty] | 0
|  |  | Pax Circulation MVZ 3 DK 11 PS SB |  | Ceiling | [16 empty] | 0
| 40 | 3 | Pax Circulation MVZ 3 DK 11 PS SB |  | Furniture |  | 0721_400_O_--_11_--_03_40_3170
|  |  | Pax Circulation MVZ 3 DK 11 PS SB |  | Furniture | [16 empty] | 0
|  |  | Pax Circulation MVZ 3 DK 11 PS SB |  | Furniture | [16 empty] | 0
|  |  | Pax Circulation MVZ 3 DK 11 PS SB |  | Furniture | [16 empty] | 0
| 40 | 4 | Passenger Flow MVZ 2 DK 11 + DK 12 PS SB |  | Lining |  | 0721_400_O_--_--_--_02_40_3250
|  |  | Passenger Flow MVZ 2 DK 11 + DK 12 PS SB |  | Lining | [16 empty] | 0
[5 empty] | Lining | [16 empty] | 0
[5 empty] | Lining | [16 empty] | 0
| 40 | 4 | Passenger Flow MVZ 2 DK 11 + DK 12 PS SB |  | Ceiling |  | 0721_400_O_--_--_--_02_40_3220
|  |  | Passenger Flow MVZ 2 DK 11 + DK 12 PS SB |  | Ceiling | [16 empty] | 0
[5 empty] | Ceiling | [16 empty] | 0
[5 empty] | Ceiling | [16 empty] | 0
| 40 | 4 | Passenger Flow MVZ 2 DK 11 + DK 12 PS SB |  | Furniture |  | 0721_400_O_--_--_--_02_40_3270
|  |  | Passenger Flow MVZ 2 DK 11 + DK 12 PS SB |  | Furniture | [16 empty] | 0
[5 empty] | Furniture | [16 empty] | 0
[5 empty] | Furniture | [16 empty] | 0
| 40 | 5 | Smoking Room MVZ 3 DK 12 |  | Lining |  | 0721_400_O_--_12_--_03_40_3150
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Lining |  |  | 230 |  | 40x20x1.5x6000 |  | Galvanized |  |  |  |  | 35 | pcs |  |  | 6.8 | 238
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Lining |  |  | 215,1 |  | 10x1200x2600 | MA-SMO-08 | Laminated |  |  |  |  | 16 | pcs |  |  | 14.2 | 227.2
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Lining |  |  | 212 |  | 20x150x20x2 | [6 empty] | 8 | m |  |  | 2.4 | 19.2
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Lining |  |  | 203,1 |  |  | MA-SMO-09 | Painted |  |  |  |  | 16.28 | m |  |  | 0.3 | 4.884
In work |  |  |  |  | Lining | [16 empty] | 0
In work |  |  |  |  | Lining | [16 empty] | 0
In work |  |  |  |  | Lining | [16 empty] | 0
In work |  |  |  |  | Lining | [16 empty] | 0
[5 empty] | Lining | [16 empty] | 0
| 40 | 5 | Smoking Room MVZ 3 DK 12 |  | Ceiling |  | 0721_400_O_--_12_--_03_40_3120
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Ceiling |  |  | 330 |  | 40x20x1.5x6000 |  | Galvanized |  |  |  |  | 3 | pcs |  |  | 6.8 | 20.4
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Ceiling |  |  | 309,1 |  | DAMPA DCC 2000-6000 Modular Carrier No. 16, L=4000 | [6 empty] | 7 | pcs |  |  | 3 | 21
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Ceiling |  |  | 317,1 |  | DAMPA DCC 2000-6000 Angle Runner No. 29, L=4000 | [6 empty] | 3 | pcs |  |  | 4.2 | 12.6
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Ceiling |  |  | P |  | Prefabricated ventilation profile + C list | MA-SMO-01 | Painted |  |  |  |  | 16 | m |  |  | 0
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Ceiling |  |  | 311,1 |  | DAMPA DCC 2000-6000 Edge Trim No. 27, L=4000 | MA-SMO-01 | Painted |  |  |  |  | 3 | pcs |  |  | 2.6 | 7.8
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Ceiling |  |  | 314,1 |  | DAMPA DCC 2000-6000 Edge Trim No. 26, L=4000 | MA-SMO-01 | Painted |  |  |  |  | 2 | pcs |  |  | 3.2 | 6.4
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Ceiling |  |  | 305,1 |  | DAMPA DCC 2000-6000 Ceiling Panel 3000x600 | MA-SMO-01 | Painted |  |  |  |  | 8 | pcs |  |  | 11.5 | 92
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Ceiling |  |  | 329,1 |  | DAMPA DCC 6000 inspection hatch 600x600 | MA-SMO-01 | Painted |  |  |  |  | 1 | pcs |  |  | 5 | 5
In work | 40 |  | Smoking Room MVZ 3 DK 12 | 12 | Ceiling |  |  | 341,1 |  | Draught stop h=800 | [6 empty] | 14 | m |  |  | 0 | 0
0
0
0
| 40 | 5 | Smoking Room MVZ 3 DK 12 |  | Furniture |  | 0721_400_O_--_12_--_03_40_3170
|  |  | Smoking Room MVZ 3 DK 12 |  | Furniture | [16 empty] | 0
[5 empty] | Furniture | [16 empty] | 0
[5 empty] | Furniture | [16 empty] | 0
| 40 | 6 | Aft Pax Staircase MVZ 3 DK 4-12 |  | Lining |  | 0721_400_O_--_--_--_03_40_3250
|  |  | Aft Pax Staircase MVZ 3 DK 4-12 |  | Lining | [16 empty] | 0
|  |  | Aft Pax Staircase MVZ 3 DK 4-12 |  | Lining | [16 empty] | 0
|  |  | Aft Pax Staircase MVZ 3 DK 4-12 |  | Lining | [16 empty] | 0
| 40 | 6 | Aft Pax Staircase MVZ 3 DK 4-12 |  | Ceiling |  | 0721_400_O_--_--_--_03_40_3220
|  |  | Aft Pax Staircase MVZ 3 DK 4-12 |  | Ceiling | [16 empty] | 0
|  |  | Aft Pax Staircase MVZ 3 DK 4-12 |  | Ceiling | [16 empty] | 0
|  |  | Aft Pax Staircase MVZ 3 DK 4-12 |  | Ceiling | [16 empty] | 0
| 40 | 6 | Aft Pax Staircase MVZ 3 DK 4-12 |  | Furniture |  | 0721_400_O_--_--_--_03_40_3270
|  |  | Aft Pax Staircase MVZ 3 DK 4-12 |  | Furniture | [16 empty] | 0
|  |  | Aft Pax Staircase MVZ 3 DK 4-12 |  | Furniture | [16 empty] | 0
|  |  | Aft Pax Staircase MVZ 3 DK 4-12 |  | Furniture | [16 empty] | 0
| 40 | 7 | Fore Pax Staircase MVZ 2 DK 4-13 |  | Lining |  | 0721_400_O_--_--_--_02_40_3150
|  |  | Fore Pax Staircase MVZ 2 DK 4-13 |  | Lining | [16 empty] | 0
|  |  | Fore Pax Staircase MVZ 2 DK 4-13 |  | Lining | [16 empty] | 0
|  |  | Fore Pax Staircase MVZ 2 DK 4-13 |  | Lining | [16 empty] | 0
| 40 | 7 | Fore Pax Staircase MVZ 2 DK 4-13 |  | Ceiling |  | 0721_400_O_--_--_--_02_40_3120
|  |  | Fore Pax Staircase MVZ 2 DK 4-13 |  | Ceiling | [16 empty] | 0
|  |  | Fore Pax Staircase MVZ 2 DK 4-13 |  | Ceiling | [16 empty] | 0
|  |  | Fore Pax Staircase MVZ 2 DK 4-13 |  | Ceiling | [16 empty] | 0
| 40 | 7 | Fore Pax Staircase MVZ 2 DK 4-13 |  | Furniture |  | 0721_400_O_--_--_--_02_40_3170
|  |  | Fore Pax Staircase MVZ 2 DK 4-13 |  | Furniture | [16 empty] | 0
|  |  | Fore Pax Staircase MVZ 2 DK 4-13 |  | Furniture | [16 empty] | 0
|  |  | Fore Pax Staircase MVZ 2 DK 4-13 |  | Furniture | [16 empty] | 0
| 40 | 8 | Passenger Flow MVZ 2 DK 5 PS + 6 PS SB |  | Lining |  | 0721_400_O_--_--_--_02_40_3350
|  |  | Passenger Flow MVZ 2 DK 5 PS + 6 PS SB |  | Lining | [16 empty] | 0
|  |  | Passenger Flow MVZ 2 DK 5 PS + 6 PS SB |  | Lining | [16 empty] | 0
|  |  | Passenger Flow MVZ 2 DK 5 PS + 6 PS SB |  | Lining | [16 empty] | 0
| 40 | 8 | Passenger Flow MVZ 2 DK 5 PS + 6 PS SB |  | Ceiling |  | 0721_400_O_--_--_--_02_40_3320
|  |  | Passenger Flow MVZ 2 DK 5 PS + 6 PS SB |  | Ceiling | [16 empty] | 0
|  |  | Passenger Flow MVZ 2 DK 5 PS + 6 PS SB |  | Ceiling | [16 empty] | 0
|  |  | Passenger Flow MVZ 2 DK 5 PS + 6 PS SB |  | Ceiling | [16 empty] | 0
| 40 | 8 | Passenger Flow MVZ 2 DK 5 PS + 6 PS SB |  | Furniture |  | 0721_400_O_--_--_--_02_40_3370
|  |  | Passenger Flow MVZ 2 DK 5 PS + 6 PS SB |  | Furniture | [16 empty] | 0
|  |  | Passenger Flow MVZ 2 DK 5 PS + 6 PS SB |  | Furniture | [16 empty] | 0
|  |  | Passenger Flow MVZ 2 DK 5 PS + 6 PS SB |  | Furniture | [16 empty] | 0
| 58 | A | Lecture_Compass Room MVZ 2 DK 11 PS |  | Outfitting |  | 0721_400_O_--_11_--_02_58_3260
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Outfitting | [16 empty] | 0
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Outfitting | [16 empty] | 0
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Outfitting | [16 empty] | 0
| 58 | A | Lecture_Compass Room MVZ 2 DK 11 PS |  | Lining |  | 0721_400_O_--_11_--_02_58_3250
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Lining | [16 empty] | 0
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Lining | [16 empty] | 0
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Lining | [16 empty] | 0
| 58 | A | Lecture_Compass Room MVZ 2 DK 11 PS |  | Ceiling |  | 0721_400_O_--_11_--_02_58_3220
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Ceiling | [16 empty] | 0
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Ceiling | [16 empty] | 0
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Ceiling | [16 empty] | 0
| 58 | A | Lecture_Compass Room MVZ 2 DK 11 PS |  | Furniture |  | 0721_400_O_--_11_--_02_58_3270
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Furniture | [16 empty] | 0
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Furniture | [16 empty] | 0
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Furniture | [16 empty] | 0
| 58 | B | Karaoke Room MVZ 2 DK 11 PS |  | Outfitting |  | 0721_400_O_--_11_--_02_58_3260
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Outfitting | [16 empty] | 0
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Outfitting | [16 empty] | 0
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Outfitting | [16 empty] | 0
| 58 | B | Karaoke Room MVZ 2 DK 11 PS |  | Lining |  | 0721_400_O_--_11_--_02_58_3250
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Lining | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Lining | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Lining | [16 empty] | 0
| 58 | B | Karaoke Room MVZ 2 DK 11 PS |  | Ceiling |  | 0721_400_O_--_11_--_02_58_3220
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Ceiling | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Ceiling | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Ceiling | [16 empty] | 0
| 58 | B | Karaoke Room MVZ 2 DK 11 PS |  | Furniture |  | 0721_400_O_--_11_--_02_58_3270
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Furniture | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Furniture | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Furniture | [16 empty] | 0
| 58 | C | Karaoke Room MVZ 2 DK 11 PS |  | Outfitting |  | 0721_400_O_--_11_--_01_58_3160
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Outfitting | [16 empty] | 0
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Outfitting | [16 empty] | 0
|  |  | Lecture_Compass Room MVZ 2 DK 11 PS |  | Outfitting | [16 empty] | 0
| 58 | C | Karaoke Room MVZ 2 DK 11 PS |  | Lining |  | 0721_400_O_--_11_--_01_58_3150
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Lining | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Lining | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Lining | [16 empty] | 0
| 58 | C | Karaoke Room MVZ 2 DK 11 PS |  | Ceiling |  | 0721_400_O_--_11_--_01_58_3120
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Ceiling | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Ceiling | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Ceiling | [16 empty] | 0
| 58 | C | Karaoke Room MVZ 2 DK 11 PS |  | Furniture |  | 0721_400_O_--_11_--_01_58_3170
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Furniture | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Furniture | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Furniture | [16 empty] | 0
| 58 | C | Karaoke Room MVZ 2 DK 11 PS |  | Furniture |  | 0721_400_O_--_11_--_01_58_3180
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Floor | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Floor | [16 empty] | 0
|  |  | Karaoke Room MVZ 2 DK 11 PS |  | Floor | [16 empty] | 0

## Revisions
Rev | Update | Date
004 | Dropdown list added for part column. Draugh stop, B-15 Extensionand exit light added to Ceiling denomination | 2019-11-27
005 | Storm rails added to steel outfitting | 2020-01-20
006 | Added Owner / Yard to drop down list | 2020-02-03
007 | Part numbers added. Visco, levelling, roller shutter, C-Glass wall and root plate added. | 2020-05-11
008 | Gypsum Board added to walls and ceilings | 2021-05-19
009 | Added Pedimat and C-glass Door to denomination | 2021-06-24
010 | Added part numbers for Visco and Levelling. A-doors added to steel outfitting. Units added for Walls and Floors. B- and C-door sheet added. | 2021-08-05
011 | Added WC-modules to steel outfitting | 2021-08-13
012 | Ceiling U-list added | 2021-09-16
013 | Floor materials added: Cement Compound, Light Concrete, Rockwool, Steel Plate and Water insulation | 2021-10-29
014 | Added vinyl adhesive, Ceiling Z-insert list, Ceiling U-end list | 2021-11-16
015 | Dots in part numbers changed to commas. | 2022-01-04
016 | Added Parquet Adhesive and Floor Modules to drop down list | 2022-01-11
017 | Added U-insert profile to ceilings | 2022-04-06
018 | Barrisol | 2022-05-13
019 | Added painted steel | 2022-08-12
020 | Added steel sheet and Angle Bar for floors (raised floor structure)
021 | Added condence profile, Walls changed to Lining | 2022-10-18
022 | Added status "partly received" and "partly onboard" to column A | 2022-10-21
023 | Adcded U-profile under Floors | 2022-10-27
024 | Added sliding door brush seal under wall denomination | 2022-11-02
025 | Added Cove Profile under floor denomination | 2023-01-19
026 | Added Angle bar L40 + flat bar to flooring, for raised floor construction | 2023-03-17

## List for enquiries
Surfaces | Status | Ceiling | Walls | Floor | Steel outfitting | Certificate | Prefab.
Galvanized |  | Ventilation grill | A-door | Anti-slip Tape | Angle bar L30 | MED | YES
Painted | In work | Angle Bar L40 | A-Glass Door | Angle Bar L40 | Angle bar L40 | Noncombust. | NO
Anodized | Engineered | Arrow-Profile | Arrow-Profile | Angle Bar L50 | Beam | Type Approval
Brushed | Inquired | Barrisol | B-15 Movable Wall | Border Profile | Border steel | ADA complient
Electrogalvanization | Ordered | Panel Ceiling | B-15 Wall extension |  | Bumber | Marine use
Laminated | Received | Cassette Ceiling | B-Glass Element | Carpet | Ceiling bracket
Coated | On Board | Ceiling Carrier | B0-Door | Cement Compound | Condence Profile
Primer | Not In Use | Ceiling Wall Carrier | B15-Door | Cove Profile | Deck hatch
Foiled | Owner/Yard | Ceiling Accesories | B15-Glass Door | Drain cover | Doubling
Wall Covering | Partly received | Ceiling Support | C-Door | Dirt Mat | Flat bar
NA | Partly On Board | Decorative Profile | C-Glass door | Epoxy | Flexible Support
Barrisol |  | Edge Moulding | C-Glass wall | Floating floor | Foundation
Vinyl |  | Front Plate | C-Profile | Levelling | Handrail
Galvanized / Foiled |  | Flat Ceiling | Decorative Profile | Light concrete | Insulation pin
Galvanized / Primered |  | Gypsum Board | Gypsum Board | Rockwool | J-Profile
Galvanized / Painted |  | Honeycomb Panel | Hardcore Panel | Skirting | Metal sheet
Galvanized / Foiled |  | Metal sheet | Laminate | Square Bar | Penetration collar
Galvanized both sides | In work | Painted steel | LLL Profile | Floor Support | Root plate
Primered both sides | Engineered | Rectangular Tube | Metal Sheet | Stair Nosing Profile | Stringer
Painted both sides | Inquired | Root plate | Painted steel | Synthetic Floor | Step
Foiled both sides | Offer received | Service Hatch | Pillar cover | Plywood | Square Tube
|  | Square Tube | Rectangular Tube | Painted Floor | Steel plate
|  | Support For Camera | Roller Shutter | Teak | Steel sheet
|  | Support For Downlight | Root plate | Threshold | Storm Rail
|  | Support For Exit Light | Service Door | Tile | Rectangular Tube
|  | Support For Lamps | Service Hatch | Underlay | U-Support Profile
|  | Support For Loudspeaker | Skirting | Vinyl Floor | Wall support
|  | Support For Sprinkler | Sliding door brush seal | Visco | Wall bracket
|  | Draught Stop | Square Tube |  | WC module
|  | B-15 Extension | Tiles |  | Washer
|  | Exit light | TV Bracket
U-profile
Ventilation grill
Wall Cassette
Wall Cassette Service Door
Wall Cassette Service Hatch
Wall Covering
Wall Support